## Sheet1
Comment Resolution Account for Business Document Envelope version 1.0
Prepared: | 2015-06-01
Comment # | Public review | Date provided | Link to email | Commenter | Comment provided / Issue raised | TC decision on resolution
TCADMIN-01 | bdx-bde-v1.0-csprd01 | 26/03/2015 | https://lists.oasis-open.org/archives/bdxr-comment/201503/msg00001.html | Chet Ensign | On the cover page, the link under the Technical Committee name goes to the UBL TC, not the BDXR TC | Comment accepted. Link has been updated.
TCADMIN-02 | bdx-bde-v1.0-csprd01 | 26/03/2015 | https://lists.oasis-open.org/archives/bdxr-comment/201503/msg00001.html | Chet Ensign | On the cover page, the Additional artifacts section should be included and it should list the mod, val, xsd and xsdrt subdirectories | Comment accepted. Additional artifacts section have been included on the cover page and lists related subdirectories.
TCADMIN-03 | bdx-bde-v1.0-csprd01 | 26/03/2015 | https://lists.oasis-open.org/archives/bdxr-comment/201503/msg00001.html | Chet Ensign | On the cover page, the namespaces should be hyperlinked. We created the namespace landing page for this publication | Comment accepted. Namespaces have been hyperlinked and now point to the landing page created by OASIS.
EPRIOR-01 | bdx-bde-v1.0-csprd01 | 24/04/2015 | https://lists.oasis-open.org/archives/bdxr-comment/201504/msg00002.html | Ole Ellerbæk Madsen | Binary files are included in the envelope, which might generate issues with very large files (parsing highly time consuming) | The BDE is content agnostic by design, meaning that the envelope does not and should no have an opinion about what goes inside. It is up to implementers to create specific policies for the content of the envelope such as if they want to limit the size and/or nature of content in specific contexts. No change required.
EPRIOR-02 | bdx-bde-v1.0-csprd01 | 24/04/2015 | https://lists.oasis-open.org/archives/bdxr-comment/201504/msg00002.html | Ole Ellerbæk Madsen | Only one receiver ID is supported, it is therefore not possible to specify several schemes (i.e. one or several receivers – recipient list, multicast) | Comment accepted. The specification has been changed to allow multiple party IDs.
EPRIOR-03 | bdx-bde-v1.0-csprd01 | 24/04/2015 | https://lists.oasis-open.org/archives/bdxr-comment/201504/msg00002.html | Ole Ellerbæk Madsen | External references do not seem to support "external attachments" using URL, file path, MIME part reference (for multi parts items) | Comment accepted. A "Payload External Reference" has been added to the specification to support the requirement.
DIGST-01 | bdx-bde-v1.0-csprd01 | 24/04/2015 | https://lists.oasis-open.org/archives/bdxr-comment/201504/msg00003.html | Ole Ellerbæk Madsen | It should be analyzed whether there are functionality in existing envelopes that can not be mapped to BDE | A complete analysis of difference in functionalities between the BDE and the SBDH has been made by the TC. A "Customization ID" has been added to the BDE specification as a result, as we have assesed that this can be useful for implementers of BDE (albeit no requirement has been raised so far). Further differences in content from the SBDH has not been added to the BDE as we believe these to be irrelevant for BDE implementers and/or offering redundant functionalities. We have instead focused on keeping the BDE schema slim and easy to implement.
TAB-1190 | bdx-bde-v1.0-csprd01 | 25/04/2015 | https://lists.oasis-open.org/archives/bdxr-comment/201504/msg00006.html | Patrick Durusau | URL Redirects | Comment accepted. Link has been changed to https://www.oasis-open.org/ as suggested.
TAB-1191 | bdx-bde-v1.0-csprd01 | 25/04/2015 | https://lists.oasis-open.org/archives/bdxr-comment/201504/msg00006.html | Patrick Durusau | Hanging Paragraphs | Comment accepted. Use of hanging paragraphs in the document has been reviewed and hanging paragraphs have been removed where suitable.
TAB-1192 | bdx-bde-v1.0-csprd01 | 25/04/2015 | https://lists.oasis-open.org/archives/bdxr-comment/201504/msg00006.html | Patrick Durusau | Normative vs. Non-Normative Text | Comment accepted. All non-normative text has moved to appendixes and clearly marked as "non-normative".
TAB-1193 | bdx-bde-v1.0-csprd01 | 25/04/2015 | https://lists.oasis-open.org/archives/bdxr-comment/201504/msg00006.html | Patrick Durusau | Keywords - Not identified/used correctly | Comment accepted. Keywords in normative sections have been changed to all caps.
TAB-1194 | bdx-bde-v1.0-csprd01 | 25/04/2015 | https://lists.oasis-open.org/archives/bdxr-comment/201504/msg00006.html | Patrick Durusau | References - RFC2119 | Comment accepted. The citation has been corrected as suggested by commenter.
TAB-1195 | bdx-bde-v1.0-csprd01 | 25/04/2015 | https://lists.oasis-open.org/archives/bdxr-comment/201504/msg00006.html | Patrick Durusau | References - XML Spec | Comment accepted. The citation has been corrected as suggested by commenter.
TAB-1196 | bdx-bde-v1.0-csprd01 | 25/04/2015 | https://lists.oasis-open.org/archives/bdxr-comment/201504/msg00006.html | Patrick Durusau | References - XML Schema Part 1 | Comment accepted. The citation has been corrected as suggested by commenter.
TAB-1197 | bdx-bde-v1.0-csprd01 | 25/04/2015 | https://lists.oasis-open.org/archives/bdxr-comment/201504/msg00006.html | Patrick Durusau | References - XML Schema Part 2 | Comment accepted. The citation has been corrected as suggested by commenter.
TAB-1198 | bdx-bde-v1.0-csprd01 | 25/04/2015 | https://lists.oasis-open.org/archives/bdxr-comment/201504/msg00006.html | Patrick Durusau | References - XMLSIG | Comment accepted. The citation has been corrected as suggested by commenter and latest XML-Signature version (1.1) has been used.
TAB-1199 | bdx-bde-v1.0-csprd01 | 25/04/2015 | https://lists.oasis-open.org/archives/bdxr-comment/201504/msg00006.html | Patrick Durusau | Uncited Normative References | Comment accepted. Keys to the normative references have been added.
TAB-1200 | bdx-bde-v1.0-csprd01 | 25/04/2015 | https://lists.oasis-open.org/archives/bdxr-comment/201504/msg00006.html | Patrick Durusau | References to undefined subdirectories | Changes implemented as follows: - "val/" directory is not related to conformance and is only an example, and so will stay in the appendix. No change required; - "art/" and "db/" directories are not related to conformance and are only in the package to support the documentation HTML and XML files. No change required; - References to "xsd/" and "xsdrt/" directories have been removed from non-normative sections and have been listed under the additional artefacts section on the cover page. References from the normative section 3 have not been changed and stay as in previous version.
TAB-1201 | bdx-bde-v1.0-csprd01 | 25/04/2015 | https://lists.oasis-open.org/archives/bdxr-comment/201504/msg00006.html | Patrick Durusau | Missing additional artifacts | Comment accepted. The list of schema files have been removed from the annex to avoid confusion as to their normative nature. The hyperlinks to the schema files from the normative section 3 of the document have been updated to point to normative versions of the artifiacts. An "additional artifacts" section has been added to the cover page.
TAB-1202 | bdx-bde-v1.0-csprd01 | 25/04/2015 | https://lists.oasis-open.org/archives/bdxr-comment/201504/msg00006.html | Patrick Durusau | Mixed Normative/Non-Normative Text - 4.4 Unqualified data type attributes | Comment partly accepted. As the BDE is based on CCTS and it provides an extension point that may include user-specified constructs also based on CCTS, the entire suite of unqualified data types must be made available in case any extension requires more than what the envelope itself is using. The documentation has been updated to clarify the availability of all of the data types to both the part of the envelope standardized by the committee and the part of the envelope agreed upon by a community of users (section 3.6).
TAB-1203 | bdx-bde-v1.0-csprd01 | 25/04/2015 | https://lists.oasis-open.org/archives/bdxr-comment/201504/msg00006.html | Patrick Durusau | Vague references - 4.5 Content data type schemas | Comment partly accepted. Content schemas have been named and hyperlinked in section "Content data type common schemas" (now section 3.5).
TAB-1204 | bdx-bde-v1.0-csprd01 | 25/04/2015 | https://lists.oasis-open.org/archives/bdxr-comment/201504/msg00006.html | Patrick Durusau | Conformance - Does not follow TC Process | Comment accepted. Conformance criteria have been numbered and listed in a bulleted list to conform with TC Process requirements.
TAB-1205 | bdx-bde-v1.0-csprd01 | 25/04/2015 | https://lists.oasis-open.org/archives/bdxr-comment/201504/msg00006.html | Patrick Durusau | Download location? Appendix A | Comment accepted. Annex A.1 has been removed.