## EDXL-TEP Issues List
OASIS Public Comments List: EDXL-Tracking of Emergency Patients (TEP) September 19, 2013 Author: Timothy Grapes
ID | Date | Raised By | Organization | Status | Section | Section Title | Document Line Number | Comment Description | Resolution
1 | 39830 | David Webber |  | Closed |  |  |  | 1) Adoption and use by the NIEM community - and particularly DoD - and how well do the schema align to NIEM: a) Why are items limited to 1023 bytes? May be interoperability issue: •tep:distinguishingMarks (1-1023) •tep:dosage (1-1023) •tep:name (1-1023) •tep:providerName (1-1023) •tep:providerDomainName (1-1023) •tep:vehicleProvider (1-1023) •tep:chiefComplaint (1-1023) •tep:twelveLeadECGInterpretation (1-1023) •tep:seriousConcerns (1-1023) | No action: The EDXL String element is limited to 1023 bytes to prevent unnecessarily verbose text strings when concise, focused information is the intention for element content. Clarification was added to the draft specification defining xml:Token in order to help understand the implication of its use.
2 | 39830 | David Webber |  | Closed |  |  |  | 1) Adoption and use by the NIEM community - and particularly DoD - and how well do the schema align to NIEM: b) element names should begin with capital letter and match representation terms | Defer: This concern is being looked at across the EDXL suite of international standards. The domain of users address by the EDXL-TEP requirements is Emergency Management, EMS and hospital communications. The current data exchange standards authority in emergency is OASIS, while the current authority in Hospitals is HL7. A current effort is underway to ensure hospital interoperability with TEP through the joint creation of a Transformation Specification which allows TEP and HL7 users to transform data for send and receive. A US Federal effort has been kicked off to address the desire for NIEM-EDXL consistency, harmonization, or compliancy.
3 | 39830 | David Webber |  | Closed |  |  |  | 1) Adoption and use by the NIEM community - and particularly DoD - and how well do the schema align to NIEM: c) what is totalGCS ? | Modification: The following clarification has been added to the specification: "The patient total Glasgow Coma Score (GCS). The GCS is a neurological scale that provides a consistent and objective method of assessing the conscious state of a person. The total score is the sum of the scores in three categories: eye opening response, verbal response, and motor response."
4 | 39830 | David Webber |  | Closed |  |  |  | 1) Adoption and use by the NIEM community - and particularly DoD - and how well do the schema align to NIEM: d) schema could use NIEM core and components from that | Defer: See response to comment # 2
5 | 39830 | David Webber |  | Closed |  |  |  | 2) HIPAA compliance and easier information policy management Attached JPG (referencing tep-image.jpg) shows the schematic of the content - notice that for policy purposes related information is not grouped under applicable parent privacy area elements - that would allow access based on need to know and context - instead they are all are the same level inside the XML structure (RED ITEMS). | No Action: After discussions with originators of requirements in the Emergency Management domain and HL7 partners, it is agreed that EDXL-TEP messaging will be exchanged between trusted secure systems that have authority to handle HIPAA sensitive data. HIPPA concerns are addressed via secure encripted communications coupled with secure, authoritative sending and receiving systems and trained, vetted users.
6 | 39830 | David Webber |  | Closed |  |  |  | 3) Alignment with other OASIS TC work - consider using newer versions of imported schema - such as CIQ v4 - and then newer geospatial. | Defer: The specification is in synchronization with the latest EDXL-Common Types, in alignment with the full suite of EDXL standards. As newer versions of CIQ and geospatial schemas are approved for use in the EDXL-Common Types, they will be applied to the EDXL-TEP specification as well as other applicable EDXL standards for consistency.
7 | 39830 | David Webber |  | Closed |  |  |  | One further note - the schema themselves contain product representations from a non-OASIS member. | No action: Insufficient information is provided to address the comment.
8 | 39834 | David Webber |  | Closed |  |  |  | Referencing email comments from David Webber under the heading "NAMING AND DESIGN RULES (NDR) ASSESSMENT" (NIEM), several elements and attributes are cited as non-compliant to the NIEM NDR. | Defer: See response to comment # 2
9 | 39834 | David Webber |  | Closed |  |  |  | •Warning - code, type, indicator or flag items with no allowed values restriction •axal:Thoroughfare/@Type •xpil:IssuerName/@OrganisationIDType •/xpil:Address/axal:PostCode •/tep:patient/tep:familyUnificationCode •/ct:Address/axal:PostCode •/ct:EDXLGeoPoliticalLocation/ct:GeoCode •/tep:providerJurisdiction/axal:PostCode •/tep:personnelJurisdiction/axal:PostCode •/tep:vehicleJurisdiction/axal:PostCode | No Action: These elements are not restricted by design to allow the flexibility needed to accommodate heterogeneous, including international, domains.
10 | 39834 | David Webber |  | Closed |  |  |  | •Warning - numeric items with no content mask •tep:source/ct:ValueListURI •tep:source/ct:Value •tep:raceEthnicity/ct:ValueListURI •tep:raceEthnicity/ct:Value •axal:Thoroughfare/axal:Number •tep:personalID/xpil:ContactNumbers •xpil:ContactNumbers/xpil:ContactNumber •xpil:ContactNumber/xpil:ContactNumberElement •tep:hairColor/ct:ValueListURI •tep:eyeColor/ct:ValueListURI •tep:fluentSpokenLanguages/ct:ValueListURI •tep:fluentSpokenLanguages/ct:Value •tep:specialTransportationNeeds/ct:ValueListURI •tep:specialTransportationNeeds/ct:Value •tep:specialMedicalNeeds/ct:ValueListURI •tep:specialMedicalNeeds/ct:Value •tep:medicationAllergies/ct:ValueListURI •tep:medicationAllergies/ct:Value •tep:name/ct:ValueListURI •tep:route/ct:ValueListURI •tep:currentMedication/tep:frequency •tep:barriersToPatientCare/ct:ValueListURI •tep:barriersToPatientCare/ct:Value •tep:patientContactInformation/xpil:ContactNumbers •tep:closestRelativeGuardianContactInformation/xpil:ContactNumbers •tep:kind/ct:ValueListURI •tep:kind/ct:Value •ct:GeoCode/ct:ValueListURI •ct:GeoCode/ct:Value •tep:providerNumber/ct:ValueListURI •tep:providerCountry/ct:ValueListURI •tep:providerKind/ct:ValueListURI •tep:providerKind/ct:Value •tep:healthCareProvider/tep:personnelIDNumber •tep:personnelCertificationLevel/ct:ValueListURI •tep:personnelCertificationLevel/ct:Value •tep:transport/tep:unitNumber •tep:vehicleKind/ct:ValueListURI •tep:locationCategory/ct:ValueListURI •tep:cardiacMonitorRhythm/ct:ValueListURI •tep:cardiacMonitorRhythm/ct:Value •tep:medicationAdministered/tep:frequency •tep:proceduresPerformed/ct:ValueListURI •tep:proceduresPerformed/ct:Value •tep:careProviderPrimaryImpression/ct:ValueListURI •tep:careProviderPrimaryImpression/ct:Value •ext:parameter/ext:value | No Action: None of the elements listed are elements that contain numeric content. It appears that a tool was used to identify elements based on numeric-identifying keywords (e.g., value, number).
11 | 39834 | David Webber |  | Closed |  |  |  | Referencing email comments from Davie Webber under the heading "EXTERNALS: Namespace URL axal urn:oasis:names:tc:emergency:edxl:ciq:1.0:xal tep urn:oasis:names:tc:emergency:EDXL:TEP:1.0 n urn:oasis:names:tc:emergency:edxl:ciq:1.0:xnl xsd http://www.w3.org/2001/XMLSchema xpil urn:oasis:names:tc:emergency:edxl:ciq:1.0:xpil as http://www.oasis-open.org/committees/cam gml http://www.opengis.net/gml/3.2 xml http://www.w3.org/XML/1998/namespace camed http://jcam.org.uk/editor ext urn:oasis:names:tc:emergency:edxl:extension:1.0 ct urn:oasis:names:tc:emergency:edxl:ct:1.0 | No action: Insufficient information is provided to address the comment.
12 |  | TEP-HL7 Transformation Specification mapping process |  | Open |  |  |  | TEP element: TepMessage.patient.specialClassification. USAGE shows "OPTIONAL; MAY be used once, but only once [0..1]". Correct usage SHOULD be 0..* to allow selection of many values. | Modification: Change the USAGE for this element to 0..* This change is determined to be SUBSTANTIVE, requiring additional public review. Even though this change is less constraining than the original 0..1, the change would break any existing exchange because a receiver would not be able to handle receipt of multiple values using the 0..1 rule.
13 |  | TEP-HL7 Transformation Specification mapping process |  | Open |  |  |  | Element "Dosage" Valid Values / Examples shows "2 per 24h". However the Dosage should only be the number of pills (for example), while the frequency should contain the occurance or rate. Therefore the Dosage example should read "2 tablets" Therefore the Frequency example should read "every 24 hours" | Modification: Change these examples as noted. These changes are determined non-substantive
14 |  | TEP-HL7 Transformation Specification mapping process |  | Open |  |  |  | Incident ID may or may not be unique, but currently does not carry designation of the authoritative "source" that created that ID. Additionally, a TEP message may contain multiple IncidentID's. In order to use IncidentID as a unique ID, add a "source" element paired with EACH ID. IncidentID is optional, but if included, the "source" is Required. | Modification: Add an element called "IncidentIDSource" to the existing Complex Type, paired with the "IncidentID" as described in the comment. This change is determined to be SUBSTANTIVE, requiring additional public review. Secondary note (Out Of Scope of this TEP SC): Ask the EM-TC whether the DE should contain the "source" of each incident ID carried by the DE?
15
16
17