Enter date that formal submission will be sent to TC Administrator
Enter a date between the formal charter submission date and the last day allowed by default
You have entered an invalid date.
Enter a date between the convener call date and the last day allowed by default
You have entered an invalid date.
Enter start date of planned face-to-face meeting
Enter date of planned teleconference meeting
Enter desired date for CfP to be issued
## TC Formation Scheduler
Technical Committee Formation Scheduler
This little spreadsheet will calculate the various milestone dates associated with starting a new Technical Committee. There are three tables provided: the first calculates from the date of submission; the second from a proposed meeting date; and the third from the Call for Participation announcement date.
Submission Date Scheduler
Enter the date planned to submit the draft charter to TC Administration in the highlighted yellow cell. The spreadsheet will then calculate the milestones, including the earliest possible dates for the first TC meeting (both teleconference and face-to-face). Additionally, you can modify the dates for member review and CfP announcements.
			Enter date of formal charter proposal submission to TC Administrator
Thu 04 Jan 1900			This is the date by which the TC Administrator must either post the draft charter for review or return with explanation for rejection
Thu 04 Jan 1900	Thu 18 Jan 1900		Enter start date for member review (last day allowed by default)

Fri 19 Jan 1900	Mon 22 Jan 1900		Convener call scheduled
Fri 26 Jan 1900			Final charter and comment resolution log due
Mon 29 Jan 1900			Call for Participation posted (last day allowed by default)

Wed 28 Feb 1900			Earliest date for first TC meeting if teleconference

Thu 15 Mar 1900			Earliest date for first TC meeting if face-to-face

TC Meeting Date Scheduler – Face-to-Face
Enter the proposed date for a face-to-face TC meeting in the yellow highlighted cell. The spreadsheet will then calculate the date by which the formal charter submission must be made to the TC Administrator.
Mon 16 Oct 1899			Date of formal charter proposal submission to TC Administrator
Sat 21 Oct 1899			This is the date by which the TC Administrator must either post the draft charter for review or return with explanation for rejection
Sat 21 Oct 1899	Sat 04 Nov 1899		Start / end dates for member review (last day allowed by default)

Sun 05 Nov 1899	Wed 08 Nov 1899		Convener call scheduled
Sun 12 Nov 1899			Final charter and comment resolution log due
Wed 15 Nov 1899			Call for Participation posted

			Earliest date for first TC meeting if face-to-face

TC Meeting Date Scheduler – Teleconference
Enter the proposed date for a teleconference TC meeting in the yellow highlighted cell. The spreadsheet will then calculate the date by which the formal charter submission must be made to the TC Administrator.
Tue 31 Oct 1899			Date of formal charter proposal submission to TC Administrator
Sun 05 Nov 1899			This is the date by which the TC Administrator must either post the draft charter for review or return with explanation for rejection
Sun 05 Nov 1899	Sun 19 Nov 1899		Start / end dates for member review (last day allowed by default)

Mon 20 Nov 1899	Thu 23 Nov 1899		Convener call scheduled
Mon 27 Nov 1899			Final charter and comment resolution log due
Thu 30 Nov 1899			Call for Participation posted

			Earliest date for first TC meeting if teleconference

Call for Participation Announcement Date Scheduler
Enter the proposed date for issuance of the Call for Participation in the yellow highlighted cell. The spreadsheet will then calculate the date by which the formal charter submission must be made to the TC Administrator, as well as the earliest dates for the first TC meeting.
Thu 30 Nov 1899			Date of formal charter proposal submission to TC Administrator
Tue 05 Dec 1899			This is the date by which the TC Administrator must either post the draft charter for review or return with explanation for rejection
Tue 05 Dec 1899	Tue 19 Dec 1899		Enter start date for member review (last day allowed by default)

Wed 20 Dec 1899	Sat 23 Dec 1899		Convener call scheduled
Wed 27 Dec 1899			Final charter and comment resolution log due
			Call for Participation posted

Mon 29 Jan 1900			Earliest date for first TC meeting if teleconference

Tue 13 Feb 1900			Earliest date for first TC meeting if face-to-face

## PR to OS Timeline
Public Review to OASIS Standard Timeline
Enter the planned or actual date of submission for public review in the yellow highlighted cell. The spreadsheet will then calculate the remaining milestones. The first half calculates the minimum time required from public review submission through to OASIS Standard ballot results. The grayed cells are used if comments were received during the public review and accounts for the 7-day waiting period. The second half is to be used if an additional 15-day public review is requested and/or required.
			Enter date of 60-day public review submission to TC Administrator
Sat 06 Jan 1900			Date by which the TC Administrator must either post the specification for review or return with explanation for rejection
Sat 06 Jan 1900	Wed 07 Mar 1900		Enter start date for 60-day public review (last day allowed by default)
Thu 08 Mar 1900	Thu 15 Mar 1900		Earliest date to request CS approval / OS Submission ballot if no comments received OR if comments received
Thu 15 Mar 1900	Thu 22 Mar 1900		Date by which the TC Administrator must either start the ballot or request additional information
Thu 22 Mar 1900	Thu 29 Mar 1900		7-day ballot close
Sun 15 Apr 1900	Sun 15 Apr 1900		Date by which the TC Chair must submit OASIS Standard Ballot submission to TC Administrator
Mon 30 Apr 1900	Mon 30 Apr 1900		Date by which the TC Administrator must accept / reject submission
Tue 01 May 1900	Tue 01 May 1900		Familiarization announcement sent to OASIS membership
Wed 16 May 1900	Wed 16 May 1900		OASIS Standard Approval ballot
Fri 01 Jun 1900	Fri 01 Jun 1900		Announcement of Ballot results to membership

			Enter date of 15-day public review submission to TC Administrator
Sat 06 Jan 1900			Date by which the TC Administrator must either post the specification for review or return with explanation for rejection
Sat 06 Jan 1900	Sun 21 Jan 1900		Enter start date for 15-day public review (last day allowed by default)
Mon 22 Jan 1900	Mon 29 Jan 1900		Earliest date to request CS approval / OS Submission ballot if no comments received OR if comments received
Mon 29 Jan 1900	Mon 05 Feb 1900		Date by which the TC Administrator must either start the ballot or request additional information
Mon 05 Feb 1900	Mon 12 Feb 1900		7-day ballot close
Thu 15 Feb 1900	Thu 15 Feb 1900		Date by which the TC Chair must submit OASIS Standard Ballot submission to TC Administrator
Wed 28 Feb 1900	Wed 28 Feb 1900		Date by which the TC Administrator must accept / reject submission
Thu 01 Mar 1900	Thu 01 Mar 1900		Familiarization announcement sent to OASIS membership
Fri 16 Mar 1900	Fri 16 Mar 1900		OASIS Standard Approval ballot
Sun 01 Apr 1900	Sun 01 Apr 1900		Announcement of Ballot results to membership