## PMRM CSDPR01
PMRM 1st Public Review CSDPR01 |  |  |  | Source Reference |  |  | Issue |  |  | Consideration | [5 empty] | Resolution |  |  | Ref data: | Status: | Open | Assigned | Addressed | Closed | Obsolete | Issue Types: | Typo/Error | Editorial/Style | Clarification | Re-write | New Material
(only cite page or line # from a PDF!)
Issue # | Issue Type | Date | Status | Line # (Start) | Range | Page | Submitter | Submitter's Comment | Proposed change | Assigned Editor | Editor's comment | Submitter's response | Discussion | Proposed disposition | Submitter's Response | TC Decision | Follow-up Action | Date
1 | Clarification | 2012-06-04 | Closed | 88 |  |  | Peter Brown | Policies and principles can be understood in two ways: - as outlined/espoused by policy-makers/lawmakers (as a precursor to regulation/legislation); - as part of an organization’s internal “vision and values” that in turn drive operations and internal procedures | Clarify definitions and use of terms "policies" and "principles" | Sabo | Replace "Policies and Principles" with "Policies" | Agreed |  | As proposed by editor |  | Agreed | Incorporate in new document | 2012-09-20
2 | Clarification | 2012-06-13 | Closed | 142 | Sec 2 & 3 | 10 | John Sabo on behalf of Jeff Stollman | helpful if the sections headings in Section 2 identically matched the activities and tasks in Figure 2 (including the numbering) | Align numbering and titles in fig.2 with task and activity titles throughout sections 2 & 3 | Sabo | Agree |  | MW: Drop "for Use Case" in title "Detailed Privacy Analysis for Use Case" | Update figure 2
3 | New Material | 2012-06-13 | Closed | General |  |  | John Sabo on behalf of Jeff Stollman | the model doesn't address the shortsightedness of anyone trying to use it; I am fearful that the model will provide a false sense of accomplishment to planners and fail to achieve its goal. | Addition of some prompting questions to the model to compel model users to probe a bit deeper? | Brown | This suggestion is comprehensive, but will require lots of TIME to fully implement. And, prompting questions simply convert the “rationale” etc declarative statements into questions. Plus, the ‘prompts’ would be inherently incomplete, which is NOT good for a formative document; and, would bulk up the doc |  |  | Add a paragraph to clarify under "Iterate process" that emphasizes the issue
4 | Clarification | 2012-06-13 | Closed | 337 | 348 | 17 | John Sabo on behalf of Jeff Stollman | Task 8 should be structured as a decomposition of the Actors identified in Task 5. Most may not decompose. But several will decompose into multiple Roles. Providing this tracking from Actor to Role is likely to force better identification of the Roles. | as per comment | Willett |  |  |  | PB: Breakdown of roles using OASIS SOA-RAF standard terminology (participants, systems, domains, etc.) |  | Agreed | Incorporate in new document. Terminology aligned with existing standards | 2012-09-20
5 | New Material | 2012-06-13 | Closed | 349 | 442 | 17 | John Sabo on behalf of Jeff Stollman | Tasks 9-14 should probably result in a table. The use of the table forces the user to account for all of the process steps and all of the data flows; it forces alignment of the privacy risks and protections for each that mere textual descriptions fail to compel. | a table showing tasks 9-14 | Sabo | After task #10 ("Identity Data Flows"), agreed to break out section 3.2 into distinct tasks for incming, internally generated and outgoing PI |  | 20-09-2012: running use case needs review | Break-out of PI flows into distinct tasks
6 | Editorial/Style | 2012-06-13 | Closed | General |  |  | John Sabo on behalf of Jeff Stollman | It would be good if the examples were more exhaustive (as if they were real). This would give a better sense of the comprehensiveness anticipated for the model. | Listing several (if not all) of the communications for the EV charging example in the table [proposed in Issue #5] would give users a better sense of how to use the model. | Jutla | No Modification at this time. We tried to keep the flowing sample use case as high level as possible as an aid to understanding the specification. Developing a more comprehensive use case can be very valuable, but that would be best done separately from the specification itself. |  |  | No change, except to fill out some of the running example use case in more detail where useful |  | Agreed | Edits made through document | 2012-09-20
7 | Re-write | 2012-06-13 | Closed | 494 |  | 22 | John Sabo on behalf of Jeff Stollman | Both Monitoring and Audit are expected (as they are referenced in the description of Enforcement), but they are not specified. | In addition to Validation PI and Certification of credentials, I suggest that there is are separate validations (Monitoring and Audit) necessary to ensure that the processes are carried out as specified in the Agreement. | Willett | The Audit function has been absorbed into the collective Service definitions. |  | Discussion of relationship between policy and control; Gail: policy informs laws, which inform controls; Dawn: policy objects could be wrong, thus not inform controls; under Audit Controls definition: add policies to the “laws and regulations” list; Stuart: need a paragraph explaining “operational privacy audit controls”. Willett will revise response; | Add new definitions for "audit controls" and "monitor" to glossary
8 | New Material | 2012-06-13 | Closed | 533 |  |  | John Sabo on behalf of Jeff Stollman | Another service consideration for Enforcement that needs to be addressed is Jurisdictional Environment. The best of contracts may not be enforceable in certain venues. And the dispute over venue may have significant bearing over what rights and duties the parties have regarding use and protection of PI and PII. Even the definitions of PI and PII will vary. Because data can so easily migrate across jurisdictional boundaries, rights cannot be protected without explicit specification of what boundaries apply. | as per comment | Willett | Current draft already stresses issues of cross-jurisdictional enforcement, etc. Additional wording may help reinforce the message |  |  | Add new paragraph based on submitter's wording, to introductory section |  | Agreed | Incorporate in new document | 2012-09-20
9 | Clarification | 2012-06-13 | Closed | 573 | 595 | 25 | John Sabo on behalf of Jeff Stollman | The example should demonstrate one-to-many relationships between the services and the activities to prevent users of the model from presuming that filling in one answer covers the waterfront. In the example given for "Log EV location" under Enforcement, it would be useful to show two responses explaining why some circumstances would prompt contacting the user and others would prompt contacting the utility. | as per comment | Jutla | Minor modification to the Enforcement example |  |  | "If location is previously rejected, but log data shows location data erroneously recorded, then notify the utility for exception action and provide notice of this to the Owner."
10 | Re-write | 2012-06-13 | Closed | 573 | 644 | 25 | John Sabo on behalf of Jeff Stollman | Tasks 15-17 might best be combined into a table to ensure alignment of interactions, functions, and risks. | as per comment | Jutla | Change the Example box to tabular format |  | TC discussion (20 Sep), revise but don't restructure as a table | simply a re-structure, no new language; illustration; |  | Agreed |  | 2012-09-20
11 | Typo/Error | 2012-06-13 | Closed | 35 | 494 | 6 | Peter F Brown | Footnote seperator too far from footnote text | Word formatting error to be corrected | Brown |  |  |  | .docx edit |  | N/A |  | 2012-10-20
12 | Clarification | 2012-06-15 | Closed |  |  |  | John Sabo on behalf of Miraslav Baca | I read the PI proposal, I think that the biometric filed must be implemented in PI especially domain of authentication, for example, which characteristics, which domain, and so on (identification is something that could not be part of PI) | To be reviewed. | Janssen | Not sure where this issue is being raised?? We do not define all the components of the parameter “PI” |  |  | No change proposed. The PI parameter is NOT exhaustively defined or delimited in the PMRM, since what is PI depends on context, jurisdiction, and sensitivity
13 | Clarification | 2012-09-20 | Closed |  |  |  | TC Meeting | Privacy Management Analysis and Privacy Architecture are clearly identified as outputs from use of the PMRM but are not clearly defined | None proposed | Brown | Add definitions to glossary |  |  | "Privacy Architecture: A collection of proposed policies and practices appropriate for a given domain resulting from use of the PMRM"; and "Privacy Management Analysis: Documentation resulting from use of the PMRM and that serves multiple Stakeholders, including privacy officers and managers, general compliance managers, and system developers"

## Statistics
Breakdown by Issue Type
Typo/Error | 1
Editorial/Style | 1
Clarification | 6
Re-write | 2
New Material | 3
Breakdown by Status
Open | 0
Assigned | 0
Closed | 13
Obselete | 0
Total of Issues | 13 | Total unresolved | 0